## Stakeholder Analysis
Stakeholder Analysis
Stakeholder Name or Group | Interest (H=High/L=Low) | Influence (H=High/L=Low) | Quadrant (auto. calc.) |  | Strongly Against | Moderately Against | Neutral | Moderate Support | Strongly Support
Highway Safety Department | H | H | IV | Current |  |  |  |  | Yes
|  |  |  | Desired |  |  |  |  | Yes
Road Development Department | H | H | IV | Current |  |  | Yes
|  |  |  | Desired |  |  |  | Yes
Local Government | H | H | IV | Current |  | Yes
|  |  |  | Desired |  |  |  |  | Yes
Other Government Departments | L | L | I | Current |  |  | Yes
|  |  |  | Desired |  |  | Yes
0
1
True
TP32 Stakeholder Analysis Template
PMCC
0
Uses:
This tool helps the teams develop a detailed sense of who the stakeholders are, how they currently feel about the project and the level of support they need to exhibit for the project to have a good chance of success.
It also helps the team begin to discover how to influence relationships and strategies that will be effective for each stakeholder.
Questions:
Who are our stakeholder?
What is their current level of support?
What is the desired level of support?
Pitfalls:
Teams have little political sensitivity
They fail to recognise the need to "share the glory"
The assumptions is that a technical solution is sufficient
They don't involve others due to time constraints
The team uses only one or two conflict resolution styles
Failure to appreciate the human side of problem solving
This tool assumes that:
1) A critical mass of supportive stakeholders is essential for a successful project.
2) Some stakeholders can be moved to a higher level of support
3) Some stakeholders may only need to be neutral for the project to have a chance for success.
Note on E3: See chart on tab 'Interest_Influence Matrix' for details on quadrants.

## Interest_Influence Matrix
Interest / Influence Matrix Description
Management Strategies per Quadrant
I. Low influence, little interested people: monitor these people and inform them frequently with high level news.
II. High influence, little interested people: keep them informed about what is going on. At the beginning of the project agree with them the frequency and communication channel they would prefer.
III. Low influence, highly interested people: keep these people regularly informed. Talk to them to ensure that no major issues are arising. These people can often be very helpful with the detail of your project.
IV. High influence, highly interested people: these are the people you must fully engage with, and make the greatest efforts to satisfy.
Interest in the Project
Level of Influence
Low
Medium
High
Medium
High
IV: Manage closely
I: Monitor
(minimum effort)
III: Keep satisfied
II: Keep informed
consulted
informed

## Influencing Strategy
Stakeholder Influencing Strategy
Name or Group | Priority (1, 2, 3) | Issues / Concerns | What could be the "Wins" for the Stakeholder | Influencing Strategy / Actions | Responsible
Road Development Department | 1 | The budget to develop the new highway around the city will be over the budget | Getting additional funds for the highway so that the other projects could go on side by side. | Getting funds from Federal Government | Federal Government
Local Government | 2 | Over the years, the local government wants to get the shared credit even if federal government will fund the whole project. | Getting shared credit to improve the reputation of local politics and the city. | Convincing the Federal Government to share the credit with local government. | Federal Government
1
1
True
TP32 Stakeholder Influencing Strategy Template
PMCC
0
Note on C3: This 'Priority' indicator can be used to help defining the sequence of actions based on the 'Interest / Influence Matrix' outcome.

## Stakeholder Questions (hidden)
Generic sample questions for stakeholders to verify assumptions
No. | Questions | Stakeholders Answer
Introductory comment: You need to know how much the stakeholder you are interviewing is knowing about the project. It may be necessary to give a brief introduction into the project or its status first.
1 | What is your initial impression of the project?
2 | What is your interest in the project?
3 | What impact of the project on your organisation do you see?
4 | What benefits do you think you will receive from the project?
5 | How would you like to be communicated to and how frequently?
6 | What would you like to see delivered from the project to help you?
7 | What do you think we need to change?
8 | What concerns you most about this project?
9 | What are the main risks you see for the project?
10 | Can I ask for your support with …?
11 | Who else do you think will be impacted?
12 | Do you know who else might have an interest in this project?
13 | How does the project relate to other projects where you are a stakeholder?
14 | How involved do you expect to be in the project?
15 | What do you expect from the project manager?
16 | In terms of the project, what is of primary concern to you time, cost or scope?
17 | Does the current progress meet your expectation?